## Sheet1
Project goal
Was the goal clear? Did you understand why they are doing this? | Clear
Did you get the impression that the presenters understood the goal? | Yes
Do you think this is too hard or easy? | Deepends on ambitions
Comments and suggestions: | I think its a well defined problem
Task and time plan
Did you understand the final result of the project? | Yes
Did you understand the phases during the project? | Vague
Is your impression that the plan is well thought out? | Yes and no
Is the plan realistic? How hard will it be to complete this plan? | Easy
Comments and suggestions: | Keep updating the plan when you figure more specifc methods
late to start implementing in week two , as it is short time. Start a bit earlier.
Evaluation/test plan Are the evaluation criteria specific? Do you know what the criteria are? | Vague
How useful is the suggested evaluation? | Useful
Is evaluation qualitative or quantitative? | Qualitative
Are the criteria realistic? How hard will it be to finish the project? | Fine
Comments and suggestions:
Risk analysis
Did you understand the risks? | Good
Are all risks “handled”? | Most
Are there missing risks? | Some, see comments
In your opinion, is the project risky? | No
Comments and suggestions: | Remember to include the risk of covid for group collaboration.
They know all the risks and they presented all those risks. This is a good point to start with.
Overall presentaion
Is the plan good? | Yes
Was the presentation clear? | Vague
Is there up- or down-scaling the plan? | Yes
Comments and suggestions: | The plan is not clear yet, but they have some good overall points. Remember to opdate the plan and leave room for some more difficult stuff in the end.