## Gantt Chart
Handwriting Recognition | [6 empty] | Group 1
PROJECT TITLE |  | Handwriting recognition |  |  |  |  | COMPANY NAME | [6 empty] | Odico
[7 empty] | DATE | [6 empty] | 2021-01-07
WBS NUMBER | TASK TITLE | TASK OWNER |  | PHASE ONE
|  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
|  |  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and definition of algorithm
1.1 | Preprocessing the single image |  | Together | bar: WEEK 1 W to WEEK 1 T
1.2 | Perfecting lines recognition (start/end, center of line) |  | Esther | bar: WEEK 1 T
1.3 | Investigate use of different colour space |  | Arturo | bar: WEEK 1 T
1.4 | Digit recognition (MINST) |  | Xianhao | bar: WEEK 1 F
1.5 | Project evaluation |  | Esther, Arturo | bar: WEEK 1 F
1.6 | Get Test data (weekend) |  | Arturo | bar: WEEK 1 F
2 | Algorithm for detection dimension
2.1 | Reading dimension of work piece |  | Esther, Xianhao | bar: WEEK 2 M to WEEK 2 T
2.2 | Identify the cut line |  | Esther, Arturo | bar: WEEK 2 W
2.3 | Evaluation with test set |  | Together | bar: WEEK 2 W to WEEK 2 T
2.4 | Improvements/ Optimisation |  | Together | bar: WEEK 2 T to WEEK 2 F
2.5 | Localising the image |  | Together | bar: WEEK 2 T to WEEK 2 F
3 | Further objectives and evaluation of model
3.1 | Writing of presentation |  | Together | bar: WEEK 3 M to WEEK 3 T
3.2 | Write report |  | Arturo, Together | bar: WEEK 3 M to WEEK 3 T
3.3 | Presentation |  | Together | bar: WEEK 3 W